## Progress Planning and Tracking
Project Name: | SP-14 Red Build Chess Game Using AI
Report Date: | 2023-01-02
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3 |  |  |  | C-Day
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2016-09-02 | 2016-09-09 | 2016-09-16 | 2016-09-23 | 2016-09-30 | 2016-10-07 | 2016-10-14 | 2016-10-21 | 2016-10-28 | 2016-11-04 | 2016-11-11 | 2016-11-18 | 2016-11-25 | 2016-12-02
Requirements | Meet with stakeholder(s) SH | 50% | Delayed but complete | Bob, Sam | 2016-09-02: 20; 2016-09-09: 12; 2016-09-16: 5
Define requirements | bar: 2016-09-02 to 2016-09-16
| Review requirements with SH | 10% |  | Bob | 2016-09-09: 10; 2016-09-16: 15
Define UI requirements | bar: 2016-09-09 to 2016-09-16
| Get sign off on requirements | 0% | Will add more figures | Tom | 2016-09-16: 5; 2016-09-23: 10; 2016-09-30: 4
Project design | Define tech required * | 0% |  | Bob | 2016-09-23: 10; 2016-09-30: 4
Research product design | bar: 2016-09-23 to 2016-09-30
| Database design | 0% |  | Harry, Tom | 2016-09-23: 5; 2016-09-30: 10; 2016-10-07: 10
| X design | 0% |  | Harry, Tom | 2016-10-07: 10; 2016-10-14: 10
| Y design | 0% |  |  | 2016-09-16: 6; 2016-09-23: 6; 2016-09-30: 10; 2016-10-07: 5; 2016-10-14: 5
| Develop working prototype | 0% |  |  | 2016-10-07: 10; 2016-10-14: 10
| Test prototype | 0% |  | Tom | 2016-10-14: 5; 2016-10-21: 10; 2016-10-28: 5
Development | Review prototype design | 0% |  |  | 2016-10-21: 8; 2016-10-28: 5; 2016-11-04: 10
| Rework requirements | 0% |  |  | 2016-10-21: 8; 2016-10-28: 10; 2016-11-04: 20; 2016-11-11: 20
| Document updated design | 0% |  |  | 2016-11-11: 10; 2016-11-18: 10
| Test product | 0% |  |  | 2016-11-04: 8; 2016-11-11: 5; 2016-11-18: 20
Final report | Presentation preparation | 0% |  |  | 2016-11-18: 15; 2016-11-25: 10; 2016-12-02: 10
| Poster preparation | 0% |  |  | 2016-12-02: 10
| Final report submission to D2L and project owner | 0% |  |  | 2016-12-02: 5
Research Product design Define UI requirements
Chess Design | research chess design design primitive UI diagram |  | Total work hours | 396 | 20 | 22 | 31 | 31 | 28 | 35 | 30 | 26 | 20 | 38 | 35 | 45 | 10 | 25
Development
* formally define how you will develop this project including source code management
Legend
Planned
Delayed
Number | Work: man hours