## Progress Planning and Tracking
Project Name: | SP-14 Red Build Chess Game Using AI
Report Date: | 2023-01-02
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3 |  |  |  | C-Day
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28
Requirements | Meet with members and select project | 100% |  | Aaron, Haige,Nicholas | 2023-01-27: 4
| Define requirements | 100% |  | Aaron | 2023-01-27: 3; 2023-02-03: 2
| Review requirements and where code will be stored | 100% |  | Aaron, Haige,Nicholas | 2023-01-27: 2; 2023-02-03: 2
| Define UI requirements | 100% |  | Nicholas | 2023-01-27: 4; 2023-02-03: 2
| Get sign off on requirements | 100% |  | Aaron | 2023-01-27: 2; 2023-02-03: 2
Chess Design | Define tech required * | 0% |  | Aaron | 2023-02-03: 3; 2023-02-10: 4; 2023-02-17: 6; 2023-02-24: 4
| Research chess design | 0% |  | Aaron, Haige,Nicholas | 2023-02-03: 4; 2023-02-10: 4; 2023-02-17: 6; 2023-02-24: 7
| Ai design | 0% |  | Haige | 2023-02-03: 4; 2023-02-10: 4; 2023-02-17: 5; 2023-02-24: 5; 2023-03-03: 6
| Design primitive UI diagram | 0% |  | Nicholas | 2023-02-10: 4; 2023-02-17: 4; 2023-02-24: 5; 2023-03-03: 5; 2023-03-10: 5
| Develop working prototype | 0% |  | Haige,Nicholas | 2023-02-24: 10; 2023-03-03: 10; 2023-03-10: 10
| Test prototype | 0% |  | Aaron, Haige,Nicholas | 2023-03-10: 5; 2023-03-17: 5; 2023-03-24: 5
Development | Review prototype design | 0% |  | Haige | 2023-03-17: 8; 2023-03-24: 5; 2023-03-31: 10
| Rework requirements | 0% |  | Aaron, Haige,Nicholas | 2023-03-17: 8; 2023-03-24: 10; 2023-03-31: 20; 2023-04-07: 20
| Document updated design | 0% |  | Aaron | 2023-04-07: 5; 2023-04-14: 5
| Test product | 0% |  | Aaron, Haige,Nicholas | 2023-03-31: 8; 2023-04-07: 5; 2023-04-14: 5
Final report | Presentation preparation | 0% |  | Aaron, Haige,Nicholas | 2023-04-14: 3; 2023-04-21: 4; 2023-04-28: 3
| Poster preparation | 0% |  | Aaron, Haige,Nicholas | 2023-04-28: 3
| Final report submission to D2L and project owner | 0% |  | Aaron, Haige,Nicholas | 2023-04-21: 10; 2023-04-28: 10
|  |  | Total work hours | 295 | 15 | 19 | 16 | 21 | 31 | 21 | 20 | 21 | 20 | 38 | 30 | 13 | 14 | 16
* formally define how you will develop this project including source code management
Legend
Planned
Delayed
Number | Work: man hours